## Summary
Site Feature Audit Tracker
Goal | Inventory site features, test each user story, document defects, fix logistical and UX issues, then retest. | Status | Count
Feature Rows | 23 | Not Tested | 0
Generated From | work/goals/site-feature-audit/feature_tracker_data.json | Pass | 23
Generated Workbook | /Users/breno/Documents/code/SITES/brenorb.github.io/outputs/019f3e2b-c0a9-73a2-bab3-c0bf76811cd3/site-feature-tracker.xlsx | Fail | 0
Last Refresh | 2026-07-07 20:23:29 UTC | Blocked | 0
Notes | Use the Features sheet as the working audit matrix. | Pending Fix | 0
|  | Fixed | 2
|  | Not Retested | 0
|  | Retest Pass | 23
|  | Value | Meaning
|  | Pass | Expected behavior matched the code and smoke test.
|  | Fail | Observed behavior diverged and needs a fix or a decision.
|  | Blocked | Could not test end-to-end without an external action or missing runtime.
|  | Pending | Issue confirmed and waiting on a code change.
|  | Fixed | Code change landed and needs or passed retest.

## Features
Feature ID | Area | Example Route | User Story | Expected Behavior | Source Files | Test Status | Issue Summary | Severity | Fix Status | Fix Commit | Retest Status | Notes
F-001 | Home | / | As a first-time visitor, I can land on the homepage and immediately understand who Breno is and where to go next. | The home layout renders logo, site title, short bio, social buttons, and primary CTA buttons to About, Writing, Talks & Media, Projects, and Contact. | _layouts/home.html; _includes/social-links.html; _config.yml | Pass |  |  | Not Needed |  | Pass | Home hero, CTA buttons, and social presentation matched the layout.
F-002 | Global Navigation | /about/ | As a visitor on any page, I can open the menu and reach the main sections, profile info, and public social links. | The hamburger menu opens a nested About submenu with profile details and enabled social links, plus links for Home, Writing, Projects, Talks & Media, Contact, and Tags. | _includes/nav.html; _data/navigation.yml; assets/js/scripts.js | Pass |  |  | Not Needed |  | Pass | Menu links rendered correctly from nav plus navigation data.
F-003 | About Page | /about/ | As a visitor, I can read a concise biography and jump from the About page into the site's key sections. | The About page renders biography copy and CTA buttons for Projects, Writing, Talks & Media, Tags, and Contact. | about/index.md; _layouts/page.html | Pass |  |  | Not Needed |  | Pass | About page biography and CTA buttons rendered as expected.
F-004 | Writing Archive | /articles/ | As a reader, I can browse the writing archive and open article posts from a dedicated listing page. | The Writing archive lists only posts whose effective content type is article, with title, excerpt, and Read More button for each item. | articles/index.md; _layouts/post-list.html; _config.yml | Pass |  |  | Not Needed |  | Pass | Writing archive rendered 11 article entries with excerpts and buttons.
F-005 | Media Archive | /media/ | As a visitor, I can browse talks, podcasts, interviews, and press mentions from one archive. | The Talks & Media archive lists only posts with content_type media, with title, excerpt, and Read More button for each item. | media/index.md; _layouts/post-list.html | Pass |  |  | Not Needed |  | Pass | Media archive rendered 39 media entries.
F-006 | Projects Archive | /projects/ | As a visitor, I can browse Breno's projects from a dedicated archive page. | The Projects archive lists only posts with content_type project, with title, excerpt, and Read More button for each item. | projects/index.md; _layouts/post-list.html | Pass |  |  | Not Needed |  | Pass | Projects archive rendered 23 project entries.
F-007 | Legacy Redirects | /posts/; /interviews/ | As a visitor using an old link, I am redirected to the current archive instead of hitting a dead end. | Legacy archive aliases render noindex canonical pages that immediately refresh to their current destinations: /posts/ -> /articles/ and /interviews/ -> /media/. | posts/index.md; interviews/index.md; _includes/head.html | Pass |  |  | Not Needed |  | Pass | Legacy aliases redirected to canonical archive URLs in browser.
F-008 | Tag Archive | /tags/ | As a reader, I can browse content by tag and jump directly to the posts under each tag. | The Tag Archive lists all tags with counts, creates anchor sections for each tag, and tag links in post metadata point to the matching section anchor. | tags/index.html; _includes/meta.html | Pass |  |  | Not Needed |  | Pass | Tags archive rendered 88 tag anchors and post lists.
F-009 | Post Template | /ftx-guilt-fear/ | As a reader, I can open an article, project, or media post and get consistent framing around the content. | The post layout renders title, date, reading time, archive-aware back button, markdown body, tags, and a tweet-share link; comments appear only when enabled. | _layouts/post.html; _includes/read-time.html; _includes/meta.html; _includes/disqus_comments.html | Pass |  |  | Not Needed |  | Pass | Post template showed title, date, reading time, back button, tags, and tweet link.
F-010 | Responsive Media Embeds | /podcast-bipa-cast-22-101-perguntas-sobre-bitcoin/ | As a visitor on a media page, I can view embedded players without the layout breaking on desktop or mobile. | Embedded iframes and videos render inside the content column, resize responsively, and the first media node gains a stable media-player anchor target. | assets/js/scripts.js; _layouts/post.html | Pass |  |  | Not Needed |  | Pass | Responsive YouTube media page rendered and received media-player anchor.
F-011 | Media Chapters | /podcast-bipa-cast-22-101-perguntas-sobre-bitcoin/ | As a media consumer, I can skim a chapter list and jump the player to the relevant timestamp. | Generated media chapter blocks render topical timestamps; clicking a timestamp seeks an embedded YouTube player or HTML5 video when supported and scrolls the player into view, otherwise the fallback anchor still points to the player block. | assets/js/scripts.js; _includes/generated/*.html | Pass | Quant Finance initially embedded a YouTube watch URL inside an iframe, which prevented chapter clicks from seeking the player. The page now uses an embed URL. | Medium | Fixed | 61b638c | Pass | Retest confirmed chapter click rewrites the iframe src with start and autoplay params on /quant-finance-investimento/.
F-012 | Transcript Appendix | /podcast-bipa-cast-22-101-perguntas-sobre-bitcoin/ | As a visitor on a transcript-backed media page, I can read a structured transcript without leaving the post. | When transcript appendix data exists, the post renders collapsible transcript sections with source, timestamps, and optional speaker labels; if the transcript starts far below the fold, a transcript jump note appears near the player. | _layouts/post.html; assets/js/scripts.js | Pass |  |  | Not Needed |  | Pass | Transcript section and transcript jump note both rendered on tested media page.
F-013 | HTML5 Video Seeking | /podcast-stealth-fountain/ | As a visitor on a media page that uses a native video element, I can use chapter timestamps to seek the local player. | When the first media node is an HTML5 video, chapter clicks update currentTime, trigger playback if possible, and preserve the same anchor-based navigation affordance. | assets/js/scripts.js; _posts/2026-04-08-podcast-stealth-fountain.md | Pass |  |  | Not Needed |  | Pass | HTML5 video chapter click updated video currentTime to the selected timestamp.
F-014 | Project Rich Content | /granola/ | As a visitor on a project page, I can read richer content blocks like diagrams, media, linked documents, and outbound project resources. | Project posts can render buttons, images, embedded media, PDF links, and Mermaid diagrams when mermaid: true is present. | _posts/2024-11-06-granola-cashu-based-exchange.md; _includes/scripts.html; _layouts/post.html | Pass |  |  | Not Needed |  | Pass | Granola project rendered iframe, linked PDF/resources, image, and Mermaid SVG.
F-015 | Contact Flow | /contact/; /contact-success/ | As a visitor who wants to reach out, I can fill out a contact form and land on a success page after submission. | The contact page renders required email, name, and message fields, a hidden honeypot field, a Formspree POST action, and a success redirect target to /contact-success/; the success page confirms delivery and links back to the form. | contact/index.md; contact-success/index.md | Pass |  |  | Not Needed |  | Pass | End-to-end browser flow verified on the current build through a local mock POST target that preserves the site form markup and redirects to /contact-success/ without sending external data.
F-016 | 404 Recovery | /this-route-should-not-exist | As a visitor who follows a bad link, I get a recovery page instead of a blank or confusing error. | The 404 page renders a plain apology message and a working recovery contact or navigation path. | 404.html; _layouts/page.html | Pass | The 404 page originally rendered mailto:?subject=Page%20not%20found because site.email is unset. It now routes users to Contact and Home instead. | High | Fixed | 105d3f4 | Pass | Retest confirmed both recovery links render correctly on /404.html.
F-017 | Metadata and SEO | /; /granola/; /posts/ | As a visitor or crawler, I receive correct titles, descriptions, canonical URLs, and social metadata for each page type. | Head tags are populated from page or site data for title, description, keywords, canonical, robots, Twitter, Open Graph, and JSON-LD; feed, sitemap, and llms links are present. | _includes/head.html; _config.yml | Pass |  |  | Not Needed |  | Pass | Canonical, description, and social metadata matched tested routes.
F-018 | Comments Toggle | /os-ordinals-devem-ser-banidos-da-blockchain-do-bitcoin-o-que-dizem-os-especialistas/ | As a reader, I only see a comments area on the small subset of pages that explicitly enable comments. | The Disqus thread container and embed scripts load only when page.comments is true; pages with comments false do not render the thread block. | _layouts/page.html; _layouts/post.html; _includes/scripts.html; _includes/disqus_comments.html | Pass |  |  | Not Needed |  | Pass | Confirmed the comments-enabled route /ordinals-devem-ser-banidos/ renders the Disqus container and scripts.
F-019 | Image Lightbox | /nao-existem-atalhos-para-uma-criptomoeda-de-preco-estavel/ | As a reader, I can open linked image assets in an overlay gallery instead of leaving the page. | Anchor tags that directly target JPG, JPEG, PNG, or GIF assets receive the image-popup class and open in the Magnific Popup gallery. | assets/js/scripts.js | Pass |  |  | Not Needed |  | Pass | Verified with a local fixture page that uses the site JS and a linked PNG asset; the anchor received image-popup and opened a visible Magnific Popup overlay.
F-020 | Motion and Scroll Enhancements | /articles/ | As a visitor, I get a small amount of navigation and scrolling polish without losing usability. | Archive items animate in with WOW.js, clicking zoombtn links triggers a fade transition class swap, and a Go Up button appears after scrolling past the trigger point. | assets/js/scripts.js; _layouts/post-list.html; _layouts/home.html; _layouts/page.html; _layouts/post.html | Pass |  |  | Not Needed |  | Pass | WOW classes were present on archive items and the Go Up container became visible after scrolling.
F-021 | Machine-readable Outputs | /feed.xml; /sitemap.xml; /llms.txt | As a reader or crawler using feed and machine-readable endpoints, I can access the site's published discovery files. | The site publishes feed.xml, sitemap.xml, and llms.txt, and links to those outputs from the page head where configured. | _includes/head.html; README.md; scripts/build-llms-ctx-full.rb | Pass |  |  | Not Needed |  | Pass | Direct checks returned HTTP 200 for /feed.xml, /sitemap.xml, and /llms.txt.
F-022 | Math Rendering | /os-7-fundamentos-do-maximalismo-do-bitcoin/ | As a reader on a math-heavy post, I can read equations rendered as math instead of raw TeX syntax. | Pages load the MathJax script when site.mathjax is enabled, and math expressions are transformed from raw source syntax into rendered output. | _layouts/post.html; _layouts/page.html; _config.yml; _posts/2023-05-26-os-7-fundamentos-do-maximalismo-do-bitcoin.md | Pass |  |  | Not Needed |  | Pass | Retest confirmed the MathJax script is present on the post route and the raw inline TeX sequence is no longer visible in page text.
F-023 | X/Twitter Embeds | /twitter-fixture.html | As a reader on a page that embeds a tweet, I can see the embedded post render instead of only a plain blockquote fallback. | The site loads widgets.js and blockquote.twitter-tweet content hydrates into an embedded widget iframe when the page contains a tweet embed. | _includes/scripts.html | Pass |  |  | Not Needed |  | Pass | Verified with a local fixture page that loads the site scripts plus widgets.js; the page rendered a Twitter widget iframe.